ALMONDSBURY NEIGHBOURHOOD PLAN STEERING GROUP

22nd September 2025

PLANNING MEETING – ALMONDSBURY PARISH COUNCIL OFFICES

PRESENT; Tony Randall (TR), Ian Christie (IC), Robert Evely (RE), Marian Bennett (MB), Sue Christie (SC)

APOLOGIES; Keith Burchell, Marlene Smith, Tony Dunhill, Fi Riches

Action updates:

- IC to take minutes of NHPSG that are on the APC website and put them on the Steering Group website – Completed but we need to check for any minutes from older meetings that can be added.

- TR to meet with Justin Morris from Bristol Zoo regarding an ecology/biodiversity survey – Meeting set for TR and MB with Justin Morris on 25th September 2025

- FR to obtain an Equalities and Safeguarding statement for use as a group and on to the website – drafted policies are completed and on the website – New Action for all to read and check for any comments.

- TD to do a financial plan for the year projecting what monies might be needed to finish the plan – completed and presented to APC where I gained full support and is awaiting sign off from full council on 7th October

- RE to share the HNA with members - completed

- RE and KB to see if we can still get a meeting with Stuart Todd from Locality or whether he has left already – to be carried over

- TD/MB to do a google search on businesses and formulate a contact list – Completed with a list developed now for the SG to use

- IC and FR to look at a survey set for use with local businesses – survey set is complete but needs a small tidy up and some pre-amble explanation at the beginning

- RE to look at another QR code when survey decided – once the survey is agreed that can be completed and added to a QR code as the residents survey was

- TR to source existing business events for NHPSG members to attend – B&I have been approached and agreed that we can be a part of their business breakfast meeting on 4th November 2025 where the details of the NP can be presented and consultation completed. MB to check the availability of Easter Compton hall for that date 0600-0830hrs. We’ll need post it notes/flip chart/questions and a presentation.

NHSG members discussed the distribution of the business survey and how the consultation with the business breakfast will run. How do we engage with The Mall businesses – RE to see if he can make contact with the management company to distribute the survey via their mailboxes.

Also agreed that the next NHSG meeting will be a public meeting to update residents on progress. The asim is to see if we can get a meting done within the Cribbs community. RE to email Alison Harvey at Clifton Rugby to enquire about meeting space for 20th October.

The group also discussed some final work to be done around the residents survey in consultation to be done with other associations and groups – young people etc.

New Actions;

- MB to check availability of EC Hall for 4th November re-business breakfast

- RE to contact Stuart Todd at Locality to see if he is still available for contact.

- RE to contact Alison Harvey at Clifton Rugby Club to look at hall availability for 20th Oct public meeting

- TR and MB to feed back on meeting with Bristol Zoo and the possibility of having biodiversity studies completed.

DONM – 20th October 2025 – venue TBC as Clifton Rugby Club – 1900hrs.